## Sheet1
Pynes Orchard & Weir Meadow Joint Funding Gang Chart
Element | Detail | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14 | Month 15 | Month 16 | Month 17 | Month 18
|  | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01
Forming Group | Agree upon forming a Joint Funding Strategy & Group. Arrange 1st meeting | bar: 2021-03-01
Legals | Finalise Option Agreement with the Church Commissioners and gain Parish Council Agreement | bar: 2021-03-01 to 2021-04-01
Prospectus | Finalise both Prospectus documents ready for use | bar: 2021-03-01 to 2021-04-01
Trust Funding | Divvy up roles for members of the group to identify and research all possible Grant making Trust Funds - National & Local - populating the Funding record spreadsheet | bar: 2021-04-01 to 2021-05-01
Local Benefactors | Draw up list of individuals to approach, together with a very specific strategy and who is best to approach who? | bar: 2021-04-01 to 2021-06-01
Trust Funding | Prioritise funding applications to be completed and submitted, both in terms of for which project is the best fit, time frame and who to undertake | bar: 2021-05-01 to 2021-09-01
Crowdfunding | Consider a Crowd funding element, and which part of the project would be most attractive beyond the village | bar: 2021-07-01 to 2021-12-01
Local fundraising | Consider ways of encouraging large local fund raising events as a means of raising funds and awareness | bar: 2021-06-01 to 2022-08-01
Review | Review progress and reprioritise accordingly | bar: 2021-08-01; 2022-02-01; 2022-08-01
Public Works Loan Board | Decide strategy on whether to take a PWLB loan for Northern Fields. Consult village. Make application if supported. | bar: 2021-09-01 to 2021-12-01